## Table 1
JHU WBS Template Definition Documentation
For Capital Projects with capitalized nodes greater than $100,000
Project template can also be used for Expense Projects. Type "Expense" should be chosen in Project Builder
WBS Element | Budget Category | Budget Amount | Capitalized or Expensed | Definition
C.170.07.9999 | Project Number
C.170.07.9999.1 | Initiation |  |  | Costs incurred before approval of project; Cannot charge cost to this node
C.170.07.9999.1.01 | Land Acquisition |  | Capitalized | Land purchases
C.170.07.9999.1.02 | Existing Conditions Survey |  | Expensed | Surveyors (including environmental and geo-technical surveys), utility locations, and buildings
C.170.07.9999.1.03 | Feasibility Study |  | Expensed | Study charges - can be analyzing multiple locations for a single purpose
C.170.07.9999.1.04 | Programming |  | Expensed | Costs associated with Identifying user needs; architect or programmer develops program needs requirement (scope of work)
C.170.07.9999.1.05 | Master Planning |  | Expensed | Consultant fees for developing a master plan
C.170.07.9999.1.06 | Other Initiation Costs |  | Expensed | Miscellaneous expenses for initiation task completion
C.170.07.9999.2 | Design |  |  | Cannot charge cost to this node
C.170.07.9999.2.01 | Prime Design Contract |  | Capitalized | Architectural or engineering contract (do not include reimbursables)
C.170.07.9999.2.02 | Other Professional Fees |  | Capitalized | Interior designers, art consultants, and other miscellaneous consultant costs
C.170.07.9999.2.03 | Reimbursables |  | Capitalized | Architectural or engineering reimbursables
C.170.07.9999.2.04 | Other Design Costs |  | Capitalized | Miscellaneous expenses associated with design (excluding reimbursables)
C.170.07.9999.3 | Preconstruction |  |  | Cannot charge cost to this node
C.170.07.9999.3.01 | Cost Estimating |  | Expensed | Cost estimating if done independently of designer or contractor
C.170.07.9999.3.02 | Preconstruction Services |  | Capitalized | Fees paid for professional preconstruction consulting services
C.170.07.9999.3.03 | Site Preparation |  | Capitalized | Cost of work required to get ready for construction
C.170.07.9999.3.04 | Regulatory Fees |  | Capitalized | Permits, Baltimore City Fees, Developer's Agreements Fees, Expeditor Fees
C.170.07.9999.3.05 | Hazardous Material Removal |  | Expensed | Asbestos, lead, mold, etc. abatement
C.170.07.9999.3.06 | Other Preconstruction Costs |  | Capitalized | Miscellaneous expenses associated with pre-construction
WBS Element | Budget Category | Budget Amount | Capitalized or Expensed | Definition
C.170.07.9999.4 | Construction |  |  | Cannot charge cost to this node
C.170.07.9999.4.01 | Prime Construction Contract |  | Capitalized | Prime contractor
C.170.07.9999.4.02 | Inspection and Testing |  | Capitalized | Third-party testing such as concrete, steel, geo-technical, and fire inspection and testing
C.170.07.9999.4.03 | Commissioning |  | Capitalized | Third-party commissioning agent (commissioning is making sure building is designed and functioning as per the design intent)
C.170.07.9999.4.04 | Controls |  | Capitalized | Controls contractor fees
C.170.07.9999.4.05 | Teledata |  | Capitalized | Independent teledata contract such as Primenet
C.170.07.9999.4.06 | Security |  | Capitalized | Card access, security systems, cameras, glass breaks fees
C.170.07.9999.4.07 | Off-site Work |  | Capitalized | Utilities, access, swing space and other "enabling" projects necessary to accomplish the primary work
C.170.07.9999.4.08 | Other Construction Costs |  | Capitalized | Miscellaneous expenses associated with construction such as elevator operator services, utility fees while asset under construction, construction cleaning services, and internal maintenance services
C.170.07.9999.5 | Ancillary |  |  | Cannot charge cost to this node
C.170.07.9999.5.01 | Furniture (Expensed) |  | Expensed | An individual item of furniture or fixture(s) with a value less than $5,000
C.170.07.9999.5.01.01 | Furniture (Capital) |  | Capitalized | All individual items of furniture on projects with capital costs over $5,000,000
c.170.07.9999.5.02 | Capitalized Equipment |  | Capitalized | All equipment above $5,000; including computer systems as a whole
c.170.07.9999.5.03 | Expensed Equipment |  | Expensed | All equipment under $5,000 includes computer and handsets
c.170.07.9999.5.04 | Moving |  | Expensed | All moving expenses internal or external
c.170.07.9999.5.05 | Security Patrol |  | Expensed | Corporate Security Guards
c.170.07.9999.5.06 | Transportation |  | Expensed | Shuttle services required due to construction
c.170.07.9999.5.07 | Other Ancillary Costs |  | Expensed | Other miscellaneous ancillary expenses such as copying, printing, office supplies, caterers, training, courier, and expense report charges (meals, mileage, parking)
C.170.07.9999.6 | Contingency |  |  | Cannot charge cost to this node
C.170.07.9999.7 | Indirect Costs |  |  | Cannot charge cost to this node
C.170.07.9999.7.01 | Audit |  | Expensed | Audit Charges
C.170.07.9999.7.02 | Project Administration |  | Expensed | Project Manager Fee
C.170.07.9999.7.03 | Infrastructure Fee |  | Expensed | Projects over $100,000 get an infrastructure fee the goes into Plant Operations budget (Homewood Only)
C.170.07.9999.7.04 | Utility Connection Fee |  | Expensed | Job charges for utility connection fees (Homewood Only)
C.170.07.9999.7.05 | Capitalized Interest |  | Capitalized | Capitalized Interest
C.170.07.9999.7.06 | Other Indirect Costs |  | Capitalized | In-house design fees, if applicable
C.170.07.9999.7.06.01 | Insurance |  | Capitalized | Specific Project Insurance JHU purchased - Workman Comp-Broker Fees/ Builder's Risk/ Professional Liability/
C.170.07.9999.7.07 | Non-Capitalized Interest |  | Expensed | Non-Capitalized Interest
C.170.07.9999.7.08 | Project Administration-Consultant | DO NOT USE | Capitalized | MGAC Project Manager Fee - DO NOT USE
C.170.07.9999.7.09 | Project Management External | DO NOT USE | Capitalized | Project Manager Fees - External (JHU projects managed by JHHS) - DO NOT USE
.